## Research Phases
| Research Phase | Timeline Suggestion (differs for each project) | Activities
Phase 1 | 1) Background and contextual research | Weeks 1 - 2 | Review our own existing evidence | Undertake external literature review | Scan new data sources | Identify stakeholders (to influence, partners and data collection)
Phase 2 | 2) Developing overarching research aims and objectives | Weeks 1 - 3 | Identify key trends and themes in data | Identify gaps in data | Develop research aims | Identify stakeholders (to influence, partners and to aid data collection)
Phase 3 | 3) Research planning | Weeks 1 - 5 | Finalise research objectives | Scope methods and draw up plan | Identify stakeholders (to influence, partners and to aid data collection) | Quality assurance - get comments from key stakeholders | Undertake risk assessment if appropriate to the subject
Phase 4 | 4) Stakeholder engagement - collaboration and buy in | Weeks 2 - 6 | Financial management and incentives | Engage key partners using plan | Agree objectives and way of working | Quality assurance - get comments from key stakeholders
Phase 4 (a) | 4a) Commission research if required | Weeks 1 - 25 | Draw up specification | Procurement | Contract in place | Manage contractors | Ensure research is accessible and inclusive
Phase 5 | 5) Refining research design | Weeks 2 - 7 | Identify contributors and test groups | Refine research questions according to objective | Design engagement approach | Ensure research is accessible and inclusive
Phase 5 (a) | 5a) Piloting | Weeks 5 - 10 | Undertake pilot or feasibility study | Collect feedback | Develop and finalise approach | Ensuring we understand the policy context of the findings | Ensure research is accessible and inclusive
Phase 6 | 6) Final research product development and release | Weeks 10 - 12 | Admin e.g. instructions, formatting, materials, printing, publicity | Ensure research is accessible and inclusive
Phase 7 | 7) Data collection | Weeks 13 - 17 | Engagement commences
Phase 7 (a) | 7a) Data management | Weeks 16 - 20 | Chasing data return | Data cleaning | Data coding (if relevant)
Phase 8 | 8) Primary data analysis | Weeks 19 -22 | Number crunching (calculations) | Identifying common themes in qualitative data | Ensuring we understand the policy context of the findings
Phase 9 | 9) Secondary data analysis | Weeks 22 - 25 | Detailed analysis, cross tabs (analysis of one question in a survey against another) based on findings from primary analysis | Identify gaps in evidence and what we don’t know - check other data sources | Drawing conclusions from the data | Ensuring we understand the policy context of the findings | Ensuring that the analysis is correct
Phase 10 | 10) Develop recommendations and/or options for action | Weeks 23 - 27 | Identify further key stakeholders | Develop recommendations in consultation with stakeholders | Identify opportunities for use of research findings and evidence collected | Quality assurance of written report
Phase 11 | 11) Reporting and dissemination | Weeks 26 - 30 | Agree dissemination method based on audience | Draft products | Release
Phase 12 | 12) Evaluation and monitoring impact | Weeks 30 - 35 | Review learning | Obtain feedback | Develop plan to monitor impact | Monitor impact

## Example
Phase |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35
Phase 1 | Background and contextual research | bar: Week 1 to Week 2
Phase 2 | Developing overarching research aims and objectives | bar: Week 1 to Week 3
Phase 3 | Research planning | bar: Week 1 to Week 5
Phase 4 | Initial stakeholder engagement - collaboration and buy in | bar: Week 2 to Week 6
Phase 4 (a) | Commission research if required | bar: Week 1 to Week 25
Phase 5 | Refining research design | bar: Week 2 to Week 7
Phase 5 (a) | Piloting | bar: Week 5 to Week 10
Phase 6 | Final research product development and release | bar: Week 10 to Week 12
Phase 7 | Data collection | bar: Week 13 to Week 17
Phase 7 (a) | Data management | bar: Week 16 to Week 20
Phase 8 | Primary data analysis | bar: Week 19 to Week 22
Phase 9 | Secondary data analysis | bar: Week 22 to Week 25
Phase 10 | Develop recommendations and/or options for action | bar: Week 23 to Week 27
Phase 11 | Reporting and dissemination | bar: Week 26 to Week 30
Phase 12 | Evaluation and monitoring impact | bar: Week 30 to Week 35