## Example
Overall task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18 | Week 19 | Week 20 | Week 21 | Week 22 | Week 23 | Week 24 | Week 25 | Week 26 | Week 27 | Week 28 | Week 29 | Week 30 | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38 | Week 39 | Week 40 | Week 41 | Week 42 | Week 43 | Week 44 | Week 45 | Week 46 | Week 47 | Week 48 | Week 49 | Week 50 | Week 51 | Week 52
Background and contextual research | Week 1: 1. Review own existing evidence 2. Undertake external literature review 3. Identify stakeholders (to influence, to work with and for data collection)
Develop overarching research aims and objectives | Week 2: 1.Develop research aims and objectives 2. Identify overarching research question 3. Draw up a plan for the project
Research/engagement planning | Week 3: 1. Identify suitable research methodology for topic and groups targetted 2. Design initial draft of questionaire/discussion guide 3. Ensure that you have considered ethics and risk and taken appropriate action; Week 28: Run own survey
Refining research/engagement approach | Week 6: 1. Get input from stakeholders on questionaire/discussion guide/pilot methodology with small group of users 2. Refine methodology using feedback
Planning to publicise research | Week 7: 1. Agree how to target communications about research 2. Produce social media and other publicity materials
Research admin | Week 9: 1. Produce information sheets 2. Copy paper surveys (if appropriate) 3. Check wording and skip logic of online surveys
Data collection | Week 11: Data collection
Data management | Week 19: 1. Transcribe interviews/focus groups 2. Clean and organise survey data for analysis
Data analysis | Week 20: 1. Read transcripts/understand survey analysis 2. Undertake descriptive analysis of survey data 3. Undertake cross tab analysis of survey data (e.g. key findings by demographics) 4. Undertake thematic analysis of qualitative data
Develop key findings and structure for report | Week 23: 1. Identify the key findings of the research 2. Workshop with colleagues how to present the findings in a report
Develop recommendations | Week 24: 1. Workshop recommendations with colleagues 2. Share draft recommendations with stakeholders and refine based on their feedback
Write report | Week 25: 1. Develop report structure 2. Write draft 3. Develop appropriate data visualisations 4. Share with colleagues and external stakeholders 5. Refine content and finalise report 6. Get sign off from manager/board
Publish report, disseminate and influence stakeholders | Week 31: 1. Publish report on website and issue press release (if appropriate) 2. Disseminate report to stakeholders 3. Influence stakeholders
Evaluation and monitor impact | Week 36: 1. Undertake initial evaluation of impact 2. Identify lessons learnt for future projects; Week 51: Undertake further evaluation of impact