## 1. Assessment
Stage one: What are you planning to do? |  | Step one: Assess your options
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
Strategic fit
1 | Is this one of your priority areas for this year? | Does it align with your priorities?
2 | Independence | Does this work fit with your statutory remit? Is it important we are involved for our reputation?
3 | Is the proposal evidence driven - assess your own existing data for this subject. | What robust evidence do you have which identifies this an issue for further exploration? Do you need to address any gaps in this data now to help you make a decision?
4 | Is the proposal evidence driven - assess any local or national sources of data for this subject | What are existing and future local healthcare plans and how will they impact your work?
5 | Does your community or local patient / public user voice groups want us to do this work? | Does this relate to your communities user voice?
6 | Do commissioners / providers want us to do this work? Or do you consider this work necessary but not supported by your local commissioners / providers? | How will you get their involvement and commitment? This is a critical stage to have important stakeholders on board. No surprises!
7 | Is anyone else working on this issue? | Are they better placed to do it or can you collaborate?
8 | Check overall fit with your strategy and other commitments on your workplan | Is your workplan balanced? Does it allow leeway to resource the unexpected?
Feasibility
9 | Resources: people | Do you have (or have access to) staff / volunteers / associates who have the expertise to undertake the work?
10 | Resources: cost | How much will it cost? Will it bring in revenue?
11 | What will be the scope / objectives of your activity? | What is possible? Will this address the concern?
Impact
12 | Identify your goal | What do you want to achieve? What experience will you improve?
13 | Equality, Diversity and Inclusion (EDI) | Do you understand your EDI impact? Consider when to undertake an Equality Impact Assessment.
14 | Does it meet local Healthwatch statutory obligation to hold the 'system' to account? | Are you supporting local people by monitoring and reviewing the commissioning and provision of local care services regarding standards of provision and whether and how they can be improved?
15 | Can you influence better outcomes? Is there a realistic chance to achieve change and an opportunity to measure that change? | What is your proposed impact on individuals/community e.g. change in commissioning services/supporting consultations/a specific outcome?
16 | Are you evaluating a service? | For example, Enter and View activity.
17 | How will you help local people? | E.g. improving health inequalities.
18 | Complete a proposal to go to your board to enable them to make a decision in line with your decision making policy.
Output: A project proposal containing enough information for your Board to make a decision.

## 2. Decision
Stage one: What are you planning to do? |  | Step two: Make your decision
Name of project:
Project goal:
| Activity | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | Check your decision making policy and ensure you comply with your process. | Reminder: a decision making process is a regulatory requirement for all local Healthwatch.
2 | Prepare a paper / report to present to your board with sufficient information for them to make a decision | If you have followed 'Step One: Options' you will have all the information you need to prepare your paper / report.
3 | Recommended: Theory of Change | Use this tool if you need help with articulating your proposed outcomes / impact.
4 | Reminder: Equality, Diversity and Inclusion | Ensure you have thoughtfully considered impact on all of your community demographics. Would an Equality Impact Assessment help you at this stage?
5 | Present to your board to enable a decision to be made | Help your board make a decision by telling them: 1. What you plan to do. 2. Your expected impact / outcomes in your communities.
6 | If your proposal is not accepted, revisit any areas requiring clarification from your board
7 | Regulatory requirement: Ensure the decision made is clearly stated in the minutes of your board meeting. | Minutes of your board meetings should be publicly accessible on your website.
Output: Board minutes made public on your website detailing your decision

## Key information
Name of project
Background (What led you to undertake this project?)
Objective (Why are we doing this?)
Goal (What difference will we make?)
Project Manager
Project Sponsor (Did someone ask us to undertake this work and is sponsoring / funding it?)
| Professional audiences (those who can influence service change as a result of your project) | Public audiences (those impacted by the service(s) covered in your project)
Key audiences (Individuals and organisations)
Timeline
Methodology (Engagement and research methods)
Communication media (How you will get your message to the widest reach possible)
Budget
| Name | Role
Team members (incl. volunteers and board) working on this project and their roles
External parties working on this project and their roles
Dependencies (Does the project rely on anything else happening to be successful?)
| Type | Date
Impact assessments | Data Protection Impact Assessment
Equality Impact Assessment
Risk Assessment

## 3. Planning
Stage two: How are you planning to do it? |  | Step three: Plan your activity
Name of project:
Project goal:
| Activity | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
Engagement
1 | Set your success indicators - these are the measures that will let you know you have achieved your outcomes | How will you know you have made a difference?
2 | Identify activities | What will you do and with whom to make change happen?
3 | Stakeholder engagement: influencers and decision makers | Do you know who your influencers and decision makers are? How will you engage and involve them throughout your project?
4 | Stakeholder engagement: audience mapping | Who are the people who will be impacted by any changes or awareness raising your project is aimed at? How will you engage and involve them throughout your project?
| Reminder | Make the most of people and networks you already know, keep them engaged and work through these to engage others.
Research
Optional section: ignore if your project does not include research activity
1 | Research objective | Are you clear about the purpose of your research? Who / what are you trying to influence? Have you involved your stakeholders to inform your research objective?
2 | Who is your audience and what are their characteristics? | Step 5 of the planning process provides you with more details on Equality, Diversity and Inclusion impact.
3 | Communication: How will you inform participants about the purpose of the research and what will you be asking? | Specific organisations / websites / focus groups / individuals. Think about how many people you need to take part and how you will reach them. How will you make your information accessible?
4 | Agree what method(s) you will employ to gather data from your agreed group of people. | Questionnaire / face to face / paper / online / telephone / interviews / focus groups
5 | Create your survey. | Healthwatch England have lots of resources to help with different aspects of research planning from resources, training and the research help desk
7 | Do you need to test your planned methods? | Pilot with a small group - perhaps your volunteers.
8 | How will you analyse and present your data? Report, infographics, briefings etc. | Plan for this now to ensure you leave enough time for analysis in your timescale.
Partnership working
Optional section: ignore if your project does not include partnership working
1 | Agree responsibilities to the partners you are collaborating with | For example, who will identify participants, collect data, analyse data, agree findings, write the report, publish the report?
2 | External partners: Agree who owns the data and the report and how each partner can use the data and findings
3 | Agree how you will work together and a process for addressing concerns if required. | Do you need to create a Memorandum of Understanding between collaborating partners?
Resources
1 | Funding | How will you manage the agreed budget (if you have an additional budget)
2 | Which staff / volunteers / board members will be involved in this project? | Are they clear on their role in this project? Do they have the skills to support this work?
3 | What knowledge and networks can help support this project? | Who can you involve with the expertise to help you succeed? Use the data you gathered in 'Step one: Options' to help you focus
Timescale
Key dates, events or deadlines to be aware of and taken into account. Set yourself up a diary system of reminders and milestones to help you monitor progress. Some ideas below - but by no means an exhaustive list
1 | Pilot activity
2 | Engagement activity
3 | Research activity
4 | Communication activity
5 | Analysis of findings
6 | Agreement of findings
7 | Date for publishing of your report
8 | Follow up actions
Communication
Engage with your stakeholders early and often to obtain relevant, useful information and ideas, and for fact finding. Plan ongoing communication to keep them informed of your progress such as: events, publications, face to face meetings, presentations, consultations, committees, formal correspondence, networking.
1 | Communicate with your stakeholders: inform, share outcomes and influence at appropriate stages. | Plan your communication with your stakeholders to ensure your message is understood and desired responses received.
2 | Communicate with your audience: raising awareness and sharing your impact. | Plan your engagement with your intended audience throughout your project.
3 | Promote your project | When do you need to engage, persuade or influence? Tailor your message.
4 | Share messages | What is your goal? Why are you communicating? What do you want people to do?
5 | Creative advertising | Website, social media, community venues (e.g. food banks), local newspapers, newsletters (council, tenant, community), local radio, leaflet drops to homes or partners who do existing drops etc.
6 | Communicate outcomes and impact: H&WBB, local council, ICS / ICP, hospital trust, CVS, HWE etc. | Consider if you need interim opportunities to share early findings with any of your stakeholders? Written reports / meetings with key decision makers / accessible information requirements. Be creative - how can you reach as many people as possible.
Data protection: see separate tab
Equality, diversity and inclusion: see separate tab
Risks: see separate tab
Output: This checklist forms your project plan detailing the actions you will take to achieve your planned impact.

## 4. Data protection
Stage two: How are you planning to do it? |  | Step four: Understand your data protection responsibilities
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | If required, complete a Data Protection Impact Assessment (DPIA). | For full details read the Data Protection guidance produced by Healthwatch England, accessible via the Resources section on its website.
2 | Consider what lawful basis you need to use to collect feedback, stories and images of individuals.
3 | Consider what lawful basis you need to use to collect special category data (including about health conditions, wellbeing and treatment)
4 | How will you anonymise any data that might identify someone effectively?
5 | Have you identified any risks in the collection or storage of personal information? What actions do you need to take to mitigate these risks?
6 | Obtain sign off of your DPIA (if you need one) from your Data Protection Officer
Output: Data Processing Impact Assessment (DPIA) or an assessment of how you will manage any personal information you collect as a result of this project.

## 5. Edi
Stage two: How are you planning to do it? |  | Step five: Understand your equality impact
Name of project:
Project goal:
| Activity | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | Complete an Equality Impact Assessment (EIA).
2 | Do you have a clear understanding of the demographics of the communities who use the services that are the subject of your project?
3 | Is this project likely to have differential impact on groups who experience discrimination or disadvantage? | Protected characteristics, poverty, caring responsibilities etc.
4 | Who do you need to speak with to ensure you have an understanding of local impact? | Groups with lived experience?
5 | Set up demographic data recording and reporting aligned to HWE categories.
6 | Ensure your survey (or other research media) allows you to understand if any one section of your community has different experiences of care to other sections.
7 | Are you accessible? Remove barriers to participation in your project. | Access to technology, access to transport, childcare etc. Those with learning needs may require support to participate.
8 | Is your information accessible? Remove barriers to participation in your project. | Large Print, Easy Read, BSL, translation services etc.
9 | Consider your proposed impact / outcomes - will they lead to increased equality or reduce barriers for groups who experience discrimination or disadvantage?
Output: Equality Impact Assessment (EIA)

## 6. Risks
Stage two: How are you planning to do it? |  | Step six: Understand your risks
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | If your project takes you to new venues: undertake venue risk assessments. (Safety and confidentiality) | When completed, share with those involved. Keep staff, volunteers and partners up to date with potential risk areas throughout your project.
2 | If your project involves activities: undertake an activity risk assessment. | When completed, share with those involved. Keep staff, volunteers and partners up to date with potential risk areas throughout your project.
3 | Is there potential for a topic in any part of the project to be distressing for your team? (Consider sensitive topics, lived experience of your team etc.) | Check individuals are prepared to take part. Is any aftercare / support required?
4 | Is the project team fully up to date with safeguarding training in case escalation is needed? | Potential for public to feedback abuse related activity - volunteers and staff engaging with the public should know what to do if this happens.
5 | Are any of the participants in your project considered vulnerable and at higher risk?
6 | Disclosure and Barring Service: Do staff and volunteers have the right level of DBS disclosure check for the activity you are undertaking?
7 | Data protection risk | Covered in data protection tab - any identified risks should be part of your overall risk assessment
8 | Reputational risk. | Does the project impact your independence, especially when collaborating with partners?
9 | Conflicts of interest. | Ensure your declarations are up to date and if a conflict is identified, appropriate mitigating actions taken and documented in board minutes.
10 | Hold regular risk status updates throughout your project. | Assess whether any new risks have arisen or identified risks require attention.
Output: Project Risk Assessment
This checklist is not exhaustive - each project is unique. Add additional lines where needed.

## 7. Delivery
Stage three: Doing it |  | Step seven: Deliver your project
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / date actioned / who actioned
1 | Promotion: Engage your target audience: public and professionals.
2 | Undertake planned activity such as collecting data.
3 | Analyse the data you have collected. | Look for any signs that different demographics may experience different levels of care
4 | Check your data analysis to ensure it is correct and the right conclusions have been drawn. | Ask someone else to check the data to provide another perspective and validate accuracy.
5 | Consider the data in context to the local and national environment. How do your findings compare? | What external factors can you draw on to further validate your analysis?
6 | Are there gaps in evidence coming through? | Do you need to rethink your approach / undertake additional work?
7 | Have you met your project aim / objective? | What are the common themes?
8 | Develop recommendations | Include your board and partners when appropriate.
9 | Write your report | Use your evidence to create a narrative that is engaging and gives a complete and accurate account of your activity.
10 | Are your recommendations clear with accountability for who is expected to action them and who will take ownership for monitoring action? | A separate action plan with timelines and review dates will help you focus on this critical impact area.
11 | Final report check | Always have a second check for grammar, spelling and presentation.
12 | Report sign off - internal | Approval from your board.
13 | Report sign off - external | Fact check from the subject of your report (organisation / service) to confirm accuracy.
Output: End of project report

## 8. Impact
Stage three: Doing it |  | Step eight: Assess and celebrate your outcomes
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | Communicate: distribute your report to those who can make a difference | Is your original distribution list sufficiently comprehensive?
2 | Request a response to your findings / recommendations. If appropriate, ensure the covering letter for your report contains details of the 20 day response requirement. | As per Regulations 44 and 45 of Local Healthwatch governing regulations: we have statutory powers - use them when needed.
3 | Meet with and agree next steps with those parties who are required to take action based on your recommendations.
4 | Plan follow up reviews to monitor your impact (check actions promised have been taken).
5 | Share report with those who helped by sharing their experiences | Report findings back to all contributors and thank them for their time and insight.
6 | Promote the report to the general public via social media, your website and press releases. | What are your key messages - how did you make a difference? What stories, facts, statistics or measures can help you convey your achievements? Get creative, how can you support your report with infographics, video story telling, animated videos etc.
7 | Do you have a strong spokesperson that can support your impact? | A service user whose life experience has been improved perhaps? Case studies / story telling can be a powerful way of sharing impact.
8 | Annual report | Write an article for your annual report now to capture your impact.
Output: Promotion of your work - meetings, press releases, social media activity, events etc.

## 9. Evaluation
Stage four: How can you do it better next time |  | Step nine: Evaluate your success
Name of project:
Project goal:
Activity |  | Suggested criteria / areas to consider | Comments / Date actioned / Who actioned
1 | Arrange a meeting for all involved in your project. | Include your partners if this project was a collaboration, or any party you think can give insight into why this project was / was not a success.
2 | Using each tab within this project checklist, talk through each of the 9 steps and discuss what went well and what could have gone better. | Create a safe environment and allow honesty without judgement or criticism.
3 | What difference did you make to your communities and the future experiences of people who use the services you covered in your project? Did providers act on your recommendations? | It is worth focusing on Step 8: Impact on the project checklist - did all your hard work pay off and result in positive outcomes in your communities?
4 | Are you present in the right places? Have you obtained insight into where / who sets the local agenda? Are you on the right boards / committees to influence the right people who have the power to change your local health and care agenda?
5 | Understand feedback and insights gained from those who you are seeking to influence such as commissioners or providers. | Take forward those insights into your next project - update this template as a reminder of how you can plan for better outcomes in future projects
6 | Create a continuous improvement environment in your team. Document those lessons learned from your meeting and refer to them for future projects. | Update your project checklist with ideas from the meeting to ensure they are not lost or forgotten.
7 | If you used the Theory of Change tool in your project, did you make changes to it that can inform how you'd produce a Theory of Change for future work?
Outputs: |  | 1. Lessons learned from undertaking the project 2. Evaluation of difference made to your communities 3. Updated project checklist